TeamVoice Shared SMS & VOIP Inbox - Build Plan Prepared for: TalkingVet Leadership - April 2026

# Executive Summary

TalkingVet's team currently uses Zoho Voice for SMS and calling, but only the Super Admin can see all agents' messages. This creates customer experience problems — double texts, missed context, and duplicated outreach.

TeamVoice solves this by building a shared inbox where every team member can see all conversations, send from their own personal number, and log calls — all in one place. Below is a phased plan to build, test, and deploy this tool.

| Estimated build time | 6–10 weeks (MVP in 3–4 weeks) |
| --- | --- |
| Core technology | Twilio (SMS + VOIP) · Node.js or Python backend · React frontend |
| Existing numbers | Port current numbers to Twilio OR use Twilio BYOC (Bring Your Own Carrier) |
| Team size needed | 1 developer (full-stack) + 1 part-time QA |
| Monthly cost (est.) | $80–$200/mo for Twilio usage (3–5 agents, moderate volume) |

# Build Phases

| Phase 1 | Twilio Setup & Number Migration |
| --- | --- |

This is the foundation — getting your existing phone numbers into Twilio so all messages route through the system.

## Option A — Port Existing Numbers (Recommended)

Number porting moves your existing phone numbers from your current carrier (e.g., Zoho, Google Voice, or a mobile carrier) to Twilio. Customers and staff keep the same numbers — no disruption.

- Submit a port request through the Twilio Console

- Provide account details from your current carrier (account number, PIN, billing address)

- Porting typically takes 5–10 business days for US mobile numbers

- During the port, both old and new systems work simultaneously — no gap in service

- Once ported, configure each number's webhook URL in Twilio to point to your app

## Option B — Twilio BYOC (Bring Your Own Carrier)

If porting is not possible (e.g., numbers are tied to a business contract), Twilio BYOC lets you keep numbers at your current carrier while routing calls through Twilio's platform via SIP trunking. Note: BYOC works for voice calls but SMS porting is still usually required for texting.

## Number → Agent Mapping

Each agent's number gets a dedicated Twilio sub-account or messaging service. A simple database table maps each number to the agent's profile:

| Agent | Phone Number (Twilio) |
| --- | --- |
| Sarah Mitchell | (512) 555-0101 |
| Jake Torres | (512) 555-0187 |
| Maria Chen | (512) 555-0223 |

| Phase 2 | Backend API & Database |
| --- | --- |

The backend is the brain — it stores every message, routes incoming texts and calls to the right agent inbox, and powers the shared view.

## Tech Stack

- Language: Node.js (Express) or Python (FastAPI) — either works well with Twilio's SDK

- Database: PostgreSQL — stores conversations, messages, agents, and call logs

- Real-time: WebSockets (Socket.io) or Twilio's Conversations API for live message updates

- Hosting: Railway, Render, or AWS — low-cost, easy to deploy

## Key Database Tables

| Table | Purpose |
| --- | --- |
| agents | Team member profiles, phone numbers, login credentials |
| contacts | Customer records with name, number, and notes |
| conversations | One record per customer thread, tracks all involved agents |
| messages | Every SMS sent/received, with agent ID, timestamp, and direction |
| calls | Call log: agent, customer, duration, outcome, timestamp |

## Core API Endpoints

- POST /webhook/sms — Twilio calls this when any agent's number receives a text; saves to DB and broadcasts to all connected clients

- POST /webhook/voice — Twilio calls this for incoming calls; rings the correct agent and logs the call

- GET /conversations — Returns all conversations, sorted by recency, for the shared inbox view

- POST /messages/send — Called when an agent sends a message; uses Twilio API to send from their specific number

- GET /calls — Returns call log for all agents

| Phase 3 | Shared Inbox Frontend |
| --- | --- |

The frontend is what your team uses every day. It's a web app (and optionally a desktop/mobile app) with a shared inbox, per-agent messaging, and call controls.

## Key Screens

- Shared Inbox — All conversations visible to everyone. Color-coded by which agent last responded. Double-text warnings appear when two agents have messaged the same customer recently.

- Conversation Thread — Full message history showing who sent each message and from which number. Any agent can reply, but it sends from their own number.

- Call Panel — Click-to-call from any conversation. Live call timer. Post-call notes. Shared call log visible to all agents.

- Agent Switcher — Each person logs in and sees their own identity, but can still view everyone's conversations.

- Admin View — See all agents, their numbers, activity summaries, and conversation assignments.

## Double-Text Prevention

This is the core problem TeamVoice solves. The system prevents double-texting through two mechanisms:

- Warning banner — When you open a conversation, a yellow warning appears if another agent replied within the last 2 hours, showing who sent it and when.

- Activity indicator — The conversation list shows which agents are involved in each thread via color-coded badges.

- Optional lock — Admins can enable a soft lock that requires one click to dismiss the warning before replying, slowing down accidental duplicates.

## Tech Stack

- Framework: React (web) — fast to build, easy to maintain

- UI Library: Tailwind CSS + shadcn/ui — clean, professional look without heavy design work

- Real-time updates: WebSocket connection to backend — messages appear instantly for all agents

- Auth: Simple email/password login (or SSO via Google if preferred)

| Phase 4 | VOIP Calling |
| --- | --- |

Calling is built on Twilio Voice. Agents call from within the app using their assigned number, so customers see a familiar caller ID.

## How It Works

- Agent clicks 'Call' next to a customer conversation in the app

- App requests a Twilio access token from the backend (valid for 1 hour)

- Twilio Voice SDK initiates the call from the agent's assigned number

- Customer sees the agent's number as caller ID — no difference from a normal call

- Call is recorded (optional) and logged to the shared call history with duration and outcome

## Features

- Click-to-call from any conversation or contact

- Inbound calls ring in the browser with a pop-up notification

- Shared call log — all agents see all call history with customer

- Optional call recording (requires disclosure to caller)

- Missed call alerts via in-app notification or SMS to the agent

| Phase 5 | Testing, QA & Launch |
| --- | --- |

Before going live, the system needs to be tested against real-world conditions — especially number porting, message routing, and the double-text detection logic.

## Pre-Launch Checklist

- Send test SMS from each agent number and confirm it appears in the shared inbox

- Verify incoming messages are routed to the correct conversation thread

- Test the double-text warning with two agents texting the same contact within minutes of each other

- Make a test call from each agent's number and confirm caller ID shows correctly

- Test missed call notification routing

- Confirm ported numbers receive messages (send from an outside number)

- Load test with 10+ concurrent conversations to verify real-time updates

- Browser testing: Chrome, Edge, Firefox, Safari

## Rollout Strategy

- Week 1: Deploy to staging with 1–2 agents testing alongside existing Zoho Voice setup

- Week 2: Expand to full team in parallel (keep Zoho active as backup)

- Week 3: Port first 1–2 numbers to Twilio; run both systems simultaneously

- Week 4: Port all numbers; decommission Zoho Voice

# Cost Estimate

All costs are estimates based on Twilio's standard pricing as of April 2026 for a 3–5 agent team at moderate SMS/call volume.

| Item | Unit Price | Est. Monthly |
| --- | --- | --- |
| Twilio phone numbers (5 agents) | $1.15/number/mo | ~$6 |
| Outbound SMS (1,000/mo) | $0.0079/message | ~$8 |
| Inbound SMS (500/mo) | $0.0079/message | ~$4 |
| Outbound voice minutes (200 min/mo) | $0.013/min | ~$3 |
| Inbound voice minutes (200 min/mo) | $0.0085/min | ~$2 |
| Backend hosting (Railway/Render) | Flat rate | ~$20 |
| Database (PostgreSQL) | Managed/hosted | ~$10 |
| Total (estimated) |  | ~$53–$80/mo |

# How Claude Can Help Build This

Because the project setup is already configured with Claude, the entire development process can be accelerated significantly. Here is what Claude can handle directly:

| Claude Can Do Today | Needs a Developer |
| --- | --- |
| ✓ Write the full backend API (Node.js or Python) | → Twilio account setup & number porting (manual process) |
| ✓ Build the React shared inbox UI | → Server deployment and DNS configuration |
| ✓ Set up the database schema and migrations | → Carrier coordination for BYOC/number transfer |
| ✓ Write Twilio webhook handlers | → Legal review of call recording disclosures |
| ✓ Build the real-time WebSocket layer | → PCI/HIPAA compliance review if needed |
| ✓ Write automated QA tests | → Final user acceptance testing with your team |

Ready to start? Open a new conversation in Cowork and say: "Let's build the TeamVoice backend" — Claude will scaffold the project and begin writing code immediately.